## Slide 1
WP4 - Dissemination and exploitation of project results
Dissemination and sustainability plan

## Slide 2
Leading partner for implementation of dissemination
Leading partner | University of Kragujevac
Starts | 15th November 2018.
Ends | 15th November 2021.
General activities | 4.1 Set-up Dissemination and exploitation plan 4.2 Design of project visual identity 4.3 Design and setup of project web site 4.4 Raising awareness for ADA 4.5 Final Conference

## Slide 3
Dissemination and sustainability plan is aimed to specify the dissemination activities, time-frame and responsibilities for their realization.
It is mainly based on Work Package 4 project specification.
Some parts of this document are subject to modification and improvements, particularly segments related to dissemination activities.
About ADA dissemination and sustainability plan

## Slide 4
ADA project website,
Serbian University/Faculty websites with information about accredited master study program,
TV and radio appearances,
Informative lectures for students at bachelor studies for master study program promotion,
Project newsletter sent regularly via email,
Communication and dissemination tools

## Slide 5
Serbian University/Faculty websites with information about LLL program,
One-day seminars for LLL program promotion,
Social networks LinkedIn, Twitter and Facebook page,
Final conference publication.
Communication and dissemination tools

## Slide 6
Total amount, intended for WP4 is 96,594.00 EUR, distributed in the following way:
Staff: 140 staff days (category 1), 145 staff days (category 2), 43 staff days (category 3) and 69 staff days (category 4). In total 52,629.00 €.
Mobility: Travels - 31, with spending 5,155.00 € for travel costs and 10,560.00 for costs of stay. In total 15,715.00 €.
Subcontracting: 28,250.00 €.
The resources – people and budget

## Slide 7
Detailed dissemination plan
Year | Activity No. | Partner | Description | Project month | Work package and Outcome no.
1 | 1 | UNIKG | Set-up Dissemination and exploitation plan | M1-3 | 4.1
1 | 2 | UNIKG | Design and setup of project web site www.ada.ac.rs | M1-3 | 4.3
1 | 3 | All partners | Design of project visual identity | M2-3 | 4.2
1 | 4 | UNIKG | Design and set-up of web site private part, which can only be accessed by the partners (using personal login and password). | M3-6 | 4.3
1 | 5 | UNIKG | Set-up selected social networks' profiles | M4 | 4.4
1 | 6 | UNIKG | Maintaining project website and updating information on results, events and activities | M3-12 | 4.3
1 | 7 | UNS, UB, UNI, UNIKG | Promotion of the project and its outcomes by using Serbian HEI partners' official websites, public appearances and social networks | M3-12 | 4.4
1 | 8 | UNIKG | Upgrading project web site with web pages related to the developed master study program | M11-12 | 4.3

## Slide 8
Detailed dissemination plan
Year | Activity No. | Partner | Description | Project month | Work package and Outcome no.
2 | 1 | UNIKG | Maintaining project website and updating information on results, events and activities | M1-12 | 4.3
2 | 2 | UNIKG | Providing information on project web site about accreditation of master study program with detailed syllabi of all courses and ECTS | M7 | 4.3
2 | 3 | UNS, UB, UNI, UNIKG | Providing information on Serbian HEI partners' web sites about accreditation of master study program with detailed syllabi of all courses and ECTS | M7 | 4.4
2 | 4 | UNS, UB, UNI, UNIKG | Preparation and printing of flyers and posters | M6-7 | 4.4
2 | 5 | All partners | Providing information about accreditation of master study program by using printed and video materials, TV and radio appearances, regular press releases, newsletters and social networks | M7-12 | 4.4
2 | 6 | All partners | Organizing a series of promotional lectures for students at bachelor studies | M7-12 | 4.4
2 | 7 | SAM | Providing information about master study program to the companies in Serbia, and its regional partners in Croatia, Slovenia, Montenegro, Bosnia and Herzegovina and European Management Association | M7-12 | 4.4

## Slide 9
Detailed dissemination plan
Year | Activity No. | Partner | Description | Project month | Work package and Outcome no.
3 | 1 | UNIKG | Maintaining project website and updating information on results, events and activities | M1-12 | 4.3
3 | 2 | UNIKG | Providing information on project web site about ADA master studies enrolment | M1 | 4.3
3 | 3 | UNS, UB, UNI, UNIKG | One-day seminar for presentation of LLL program | M1-2 | 4.4
3 | 4 | UNIKG | Providing information on project web site about LLL program | M1-2 | 4.3
3 | 5 | UNS, UB, UNI, UNIKG | Providing information on Serbian HEI partners' web sites about LLL program | M1-2 | 4.4
3 | 6 | UNS, UB, UNI, UNIKG | Providing information about LLL programs by using printed and video materials, TV and radio appearances, regular press releases, newsletters and social networks | M1-2 | 4.4
3 | 7 | UNS, UB, UNI, UNIKG | Providing information on project web site about participants' experience on LLL program | M9-10 | 4.3

## Slide 10
Detailed dissemination plan
Year | Activity No. | Partner | Description | Project month | Work package and Outcome no.
3 | 8 | UNS, UB, UNI, UNIKG | Providing information on project web site about students' experience with ADA master studies | M11-12 | 4.3
3 | 9 | UB | Translation and printing of Final Report | M9-12 | 4.5
3 | 10 | UNI | Printing of promotion material for the final conference | M9-12 | 4.5
3 | 11 | UNIKG | Final report publication on project website | M12 | 4.5